## Sheet1
|  | Task | No of Men | No Of Days | Start Date | Finish date
|  | Dates |  |  | 2026-09-01 | 2026-11-20
|  | Cable delivery 1 |  | 1 | 2026-10-01 | 2026-10-01
|  | Cable delivery 2 |  | 1 | 2026-10-02 | 2026-10-02
|  | Cable delivery 3 |  | 1 | 2026-10-15 | 2026-10-15
|  | Cable delivery 4 |  | 1 | 2026-10-16 | 2026-10-16
|  | Initial Works |  | 28 | 2026-10-01 | 2026-11-09
|  | Manufacturing & installation of containment | 6 | 23 | 2026-09-01 | 2026-10-01
|  | Moving of Existing whips | 8 | 20 | 2026-09-01 | 2026-09-28
|  | Delivery 1 Reciving of Whip cables transporting to Electrical rooms | 4 | 1 | 2026-10-01 | 2026-10-16
|  | Delivery 2 Reciving of Whip cables transporting to Electrical rooms |  | 1 | 2026-10-01 | 2026-10-16
|  | Delivery 3 Reciving of Whip cables transporting to Electrical rooms |  | 1 | 2026-10-01 | 2026-10-16
|  | Delivery 4 Reciving of Whip cables transporting to Electrical rooms |  | 1 | 2026-10-01 | 2026-10-16
|  | Delivery 1 Temp. Labeling of Whip cables |  | 5 | 2026-10-01 | 2026-10-07
|  | Delivery 2 Temp. Labeling of Whip cables |  | 5 | 2026-10-01 | 2026-10-07
|  | Delivery 3 Temp. Labeling of Whip cables |  | 5 | 2026-10-01 | 2026-10-07
|  | Delivery 4 Temp. Labeling of Whip cables |  | 5 | 2026-10-01 | 2026-10-07
Phases
|  | Phase 1 | 24 |  | 2026-10-01 | 2026-10-14
|  | Phase 2 | 24 |  | 2026-10-15 | 2026-10-28
|  | Phase 3 | 24 |  | 2026-10-29 | 2026-11-11
|  | Phase 4 | 12 |  | 2026-11-12 | 2026-11-20
DH 1-1
#REF! | #REF! | DH 1_1 - Panel 7 |  | 11 | 2026-10-01 | 2026-10-12 |  | 2026-10-02
#REF! | #REF! | DH 1_1 - Panel 9 |  | 13 | 2026-10-01 | 2026-10-14 |  | 2026-10-02
#REF! | #REF! | DH 1_1 - Panel 15 |  | 11 | 2026-10-01 | 2026-10-12 |  | 2026-10-15
#REF! | #REF! | DH 1_1 - Panel 17 |  | 13 | 2026-10-01 | 2026-10-14 |  | 2026-10-15
#REF! | #REF! | DH 1_1 - Panel 19 |  | 8 | 2026-10-15 | 2026-10-23 |  | 2026-10-29
#REF! | #REF! | DH 1_1 - Panel 21 |  | 13 | 2026-10-15 | 2026-10-28 |  | 2026-10-29
#REF! | #REF! | DH 1_1 - Panel 23 |  | 8 | 2026-10-15 | 2026-10-23 |  | 2026-11-12
#REF! | #REF! | DH 1_1 - Panel 25 |  | 13 | 2026-10-15 | 2026-10-28 |  | 2026-11-12
#REF! | #REF! | DH 1_1 - Panel 27 |  | 8 | 2026-10-29 | 2026-11-06 |  | 2026-11-26
#REF! | #REF! | DH 1_1 - Panel 31 |  | 13 | 2026-10-29 | 2026-11-11 |  | 2026-11-26
#REF! | #REF! | DH 1_1 - Panel 33 |  | 8 | 2026-10-29 | 2026-11-06 |  | 2026-12-10
#REF! | #REF! | DH 1_1 - Panel 39 |  | 13 | 2026-10-29 | 2026-11-11 |  | 2026-12-10
#REF! | #REF! | DH 1_1 - Panel 41 |  | 8 | 2026-11-12 | 2026-11-20 |  | 2026-12-24
#REF! | #REF! | DH 1_1 - Panel 45 |  | 13 | 2026-11-12 | 2026-11-25 |  | 2027-01-04
#REF! | #REF! | DH 1_1 - Panel 47 |  | 8 | 2026-11-12 | 2026-11-20 |  | 2027-01-04
DH 2-2
#REF! | #REF! | DH 2_2 - Panel 9 |  | 11 | 2026-10-01 | 2026-10-12 |  | 2026-10-02
#REF! | #REF! | DH 2_2 - Panel 17 |  | 13 | 2026-10-01 | 2026-10-14 |  | 2026-10-02
#REF! | #REF! | DH 2_2 - Panel 21 |  | 11 | 2026-10-01 | 2026-10-12 |  | 2026-10-15
#REF! | #REF! | DH 2_2 - Panel 23 |  | 13 | 2026-10-01 | 2026-10-14 |  | 2026-10-15
#REF! | #REF! | DH 2_2 - Panel 27 |  | 8 | 2026-10-15 | 2026-10-23 |  | 2026-10-29
#REF! | #REF! | DH 2_2 - Panel 31 |  | 13 | 2026-10-15 | 2026-10-28 |  | 2026-10-29
#REF! | #REF! | DH 2_2 - Panel 33 |  | 8 | 2026-10-15 | 2026-10-23 |  | 2026-11-12
#REF! | #REF! | DH 2_2 - Panel 35 |  | 13 | 2026-10-15 | 2026-10-28 |  | 2026-11-12
#REF! | #REF! | DH 2_2 - Panel 39 |  | 8 | 2026-10-29 | 2026-11-06 |  | 2026-11-26
#REF! | #REF! | DH 2_2 - Panel 41 |  | 13 | 2026-10-29 | 2026-11-11 |  | 2026-11-26
#REF! | #REF! | DH 2_2 - Panel 45 |  | 8 | 2026-10-29 | 2026-11-06 |  | 2026-12-10
#REF! | #REF! | DH 2_2 - Panel 47 |  | 13 | 2026-10-29 | 2026-11-11 |  | 2026-12-10
DH 1-1
|  | Panel 7- 72 No Cables |  | 11 | 2026-10-01 | 2026-10-12 | 1
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-01 | 2026-10-01
|  | Pull in Primary Circuits |  | 1 | 2026-10-01 | 2026-10-01
|  | Pull in Catcher circuits |  | 2 | 2026-10-02 | 2026-10-05
|  | Tie down of Primary circuits |  | 2 | 2026-10-06 | 2026-10-07
|  | Tie down of catcher circuits |  | 3 | 2026-10-06 | 2026-10-08
|  | Testing of Cables |  | 1 | 2026-10-09 | 2026-10-09
|  | QC of Aisle |  | 1 | 2026-10-09 | 2026-10-09
|  | Upload Fit |  | 1 | 2026-10-12 | 2026-10-12
|  | Panel 9- 84 No Cables |  | 13 | 2026-10-01 | 2026-10-14
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-01 | 2026-10-01
|  | Pull in Primary Circuits |  | 1 | 2026-10-01 | 2026-10-01
|  | Pull in Catcher circuits |  | 2 | 2026-10-02 | 2026-10-05
|  | Tie down of Primary circuits |  | 2 | 2026-10-09 | 2026-10-12
|  | Tie down of catcher circuits |  | 3 | 2026-10-09 | 2026-10-13
|  | Testing of Cables |  | 1 | 2026-10-14 | 2026-10-14
|  | QC of Aisle |  | 1 | 2026-10-14 | 2026-10-14
|  | Upload Fit |  | 1 | 2026-10-14 | 2026-10-14
| SiteFIT - Ensure DH 1-1 support bracket installed prior to cable pull U bracket to be ordered | Panel 15- 64 No Cables |  | 11 | 2026-10-01 | 2026-10-12
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-01 | 2026-10-01
|  | Pull in Primary Circuits |  | 1 | 2026-10-01 | 2026-10-01
|  | Pull in Catcher circuits |  | 2 | 2026-10-02 | 2026-10-05
|  | Tie down of Primary circuits |  | 2 | 2026-10-06 | 2026-10-07
|  | Tie down of catcher circuits |  | 3 | 2026-10-06 | 2026-10-08
|  | Testing of Cables |  | 1 | 2026-10-09 | 2026-10-09
|  | QC of Aisle |  | 1 | 2026-10-09 | 2026-10-09
|  | Upload Fit |  | 1 | 2026-10-12 | 2026-10-12
|  | Panel 17- 92 No Cables |  | 13 | 2026-10-01 | 2026-10-14
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-01 | 2026-10-01
|  | Pull in Primary Circuits |  | 1 | 2026-10-01 | 2026-10-01
|  | Pull in Catcher circuits |  | 2 | 2026-10-02 | 2026-10-05
|  | Tie down of Primary circuits |  | 2 | 2026-10-09 | 2026-10-12
|  | Tie down of catcher circuits |  | 3 | 2026-10-09 | 2026-10-13
|  | Testing of Cables |  | 1 | 2026-10-14 | 2026-10-14
|  | QC of Aisle |  | 1 | 2026-10-14 | 2026-10-14
|  | Upload Fit |  | 1 | 2026-10-14 | 2026-10-14
|  | Panel 19- 88 No Cables |  | 8 | 2026-10-15 | 2026-10-23 | 2
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-15 | 2026-10-15
|  | Pull in Primary Circuits |  | 1 | 2026-10-15 | 2026-10-15
|  | Pull in Catcher circuits |  | 2 | 2026-10-16 | 2026-10-19
|  | Tie down of Primary circuits |  | 2 | 2026-10-20 | 2026-10-21
|  | Tie down of catcher circuits |  | 3 | 2026-10-20 | 2026-10-22
|  | Testing of Cables |  | 1 | 2026-10-23 | 2026-10-23
|  | QC of Aisle |  | 1 | 2026-10-23 | 2026-10-23
|  | Upload Fit |  | 1 | 2026-10-23 | 2026-10-23
|  | Panel 21- 80 No Cables |  | 13 | 2026-10-15 | 2026-10-28
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-15 | 2026-10-15
|  | Pull in Primary Circuits |  | 1 | 2026-10-15 | 2026-10-15
|  | Pull in Catcher circuits |  | 2 | 2026-10-16 | 2026-10-19
|  | Tie down of Primary circuits |  | 2 | 2026-10-23 | 2026-10-26
|  | Tie down of catcher circuits |  | 3 | 2026-10-23 | 2026-10-27
|  | Testing of Cables |  | 1 | 2026-10-28 | 2026-10-28
|  | QC of Aisle |  | 1 | 2026-10-28 | 2026-10-28
|  | Upload Fit |  | 1 | 2026-10-28 | 2026-10-28
|  | Panel 23- 76 No Cables |  | 8 | 2026-10-15 | 2026-10-23
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-15 | 2026-10-15
|  | Pull in Primary Circuits |  | 1 | 2026-10-15 | 2026-10-15
|  | Pull in Catcher circuits |  | 2 | 2026-10-16 | 2026-10-19
|  | Tie down of Primary circuits |  | 2 | 2026-10-20 | 2026-10-21
|  | Tie down of catcher circuits |  | 3 | 2026-10-20 | 2026-10-22
|  | Testing of Cables |  | 1 | 2026-10-23 | 2026-10-23
|  | QC of Aisle |  | 1 | 2026-10-23 | 2026-10-23
|  | Upload Fit |  | 1 | 2026-10-23 | 2026-10-23
|  | Panel 25- 12 No Cables |  | 13 | 2026-10-15 | 2026-10-28
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-15 | 2026-10-15
|  | Pull in Primary Circuits |  | 1 | 2026-10-15 | 2026-10-15
|  | Pull in Catcher circuits |  | 2 | 2026-10-16 | 2026-10-19
|  | Tie down of Primary circuits |  | 2 | 2026-10-23 | 2026-10-26
|  | Tie down of catcher circuits |  | 3 | 2026-10-23 | 2026-10-27
|  | Testing of Cables |  | 1 | 2026-10-28 | 2026-10-28
|  | QC of Aisle |  | 1 | 2026-10-28 | 2026-10-28
|  | Upload Fit |  | 1 | 2026-10-28 | 2026-10-28
|  | Panel 27- 76 No Cables |  | 8 | 2026-10-29 | 2026-11-06 | 3
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-29 | 2026-10-29
|  | Pull in Primary Circuits |  | 1 | 2026-10-29 | 2026-10-29
|  | Pull in Catcher circuits |  | 2 | 2026-10-30 | 2026-11-02
|  | Tie down of Primary circuits |  | 2 | 2026-11-03 | 2026-11-04
|  | Tie down of catcher circuits |  | 3 | 2026-11-03 | 2026-11-05
|  | Testing of Cables |  | 1 | 2026-11-06 | 2026-11-06
|  | QC of Aisle |  | 1 | 2026-11-06 | 2026-11-06
|  | Upload Fit |  | 1 | 2026-11-06 | 2026-11-06
|  | Panel 31- 80 No Cables |  | 13 | 2026-10-29 | 2026-11-11
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-29 | 2026-10-29
|  | Pull in Primary Circuits |  | 1 | 2026-10-29 | 2026-10-29
|  | Pull in Catcher circuits |  | 2 | 2026-10-30 | 2026-11-02
|  | Tie down of Primary circuits |  | 2 | 2026-11-06 | 2026-11-09
|  | Tie down of catcher circuits |  | 3 | 2026-11-06 | 2026-11-10
|  | Testing of Cables |  | 1 | 2026-11-11 | 2026-11-11
|  | QC of Aisle |  | 1 | 2026-11-11 | 2026-11-11
|  | Upload Fit |  | 1 | 2026-11-11 | 2026-11-11
|  | Panel 33- 88 No Cables |  | 8 | 2026-10-29 | 2026-11-06
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-29 | 2026-10-29
|  | Pull in Primary Circuits |  | 1 | 2026-10-29 | 2026-10-29
|  | Pull in Catcher circuits |  | 2 | 2026-10-30 | 2026-11-02
|  | Tie down of Primary circuits |  | 2 | 2026-11-03 | 2026-11-04
|  | Tie down of catcher circuits |  | 3 | 2026-11-03 | 2026-11-05
|  | Testing of Cables |  | 1 | 2026-11-06 | 2026-11-06
|  | QC of Aisle |  | 1 | 2026-11-06 | 2026-11-06
|  | Upload Fit |  | 1 | 2026-11-06 | 2026-11-06
|  | Panel 39- 76 No Cables |  | 13 | 2026-10-29 | 2026-11-11
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-29 | 2026-10-29
|  | Pull in Primary Circuits |  | 1 | 2026-10-29 | 2026-10-29
|  | Pull in Catcher circuits |  | 2 | 2026-10-30 | 2026-11-02
|  | Tie down of Primary circuits |  | 2 | 2026-11-06 | 2026-11-09
|  | Tie down of catcher circuits |  | 3 | 2026-11-06 | 2026-11-10
|  | Testing of Cables |  | 1 | 2026-11-11 | 2026-11-11
|  | QC of Aisle |  | 1 | 2026-11-11 | 2026-11-11
|  | Upload Fit |  | 1 | 2026-11-11 | 2026-11-11
|  | Panel 41- 68 No Cables |  | 8 | 2026-11-12 | 2026-11-20 | 4
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-11-12 | 2026-11-12
|  | Pull in Primary Circuits |  | 1 | 2026-11-12 | 2026-11-12
|  | Pull in Catcher circuits |  | 2 | 2026-11-13 | 2026-11-16
|  | Tie down of Primary circuits |  | 2 | 2026-11-17 | 2026-11-18
|  | Tie down of catcher circuits |  | 3 | 2026-11-17 | 2026-11-19
|  | Testing of Cables |  | 1 | 2026-11-20 | 2026-11-20
|  | QC of Aisle |  | 1 | 2026-11-20 | 2026-11-20
|  | Upload Fit |  | 1 | 2026-11-20 | 2026-11-20
|  | Panel 45- 84 No Cables |  | 13 | 2026-11-12 | 2026-11-25
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-11-12 | 2026-11-12
|  | Pull in Primary Circuits |  | 1 | 2026-11-12 | 2026-11-12
|  | Pull in Catcher circuits |  | 2 | 2026-11-13 | 2026-11-16
|  | Tie down of Primary circuits |  | 2 | 2026-11-20 | 2026-11-23
|  | Tie down of catcher circuits |  | 3 | 2026-11-20 | 2026-11-24
|  | Testing of Cables |  | 1 | 2026-11-25 | 2026-11-25
|  | QC of Aisle |  | 1 | 2026-11-25 | 2026-11-25
|  | Upload Fit |  | 1 | 2026-11-25 | 2026-11-25
|  | Panel 47- 76 No Cables |  | 8 | 2026-11-12 | 2026-11-20
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-11-12 | 2026-11-12
|  | Pull in Primary Circuits |  | 1 | 2026-11-12 | 2026-11-12
|  | Pull in Catcher circuits |  | 2 | 2026-11-13 | 2026-11-16
|  | Tie down of Primary circuits |  | 2 | 2026-11-17 | 2026-11-18
|  | Tie down of catcher circuits |  | 3 | 2026-11-17 | 2026-11-19
|  | Testing of Cables |  | 1 | 2026-11-20 | 2026-11-20
|  | QC of Aisle |  | 1 | 2026-11-20 | 2026-11-20
|  | Upload Fit |  | 1 | 2026-11-20 | 2026-11-20
DH 2-2
|  | Panel 9- 56 No Cables |  |  | 2026-10-01 | 2026-10-09 | 1
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-01 | 2026-10-01
|  | Pull in Primary Circuits |  | 1 | 2026-10-01 | 2026-10-01
|  | Pull in Catcher circuits |  | 2 | 2026-10-02 | 2026-10-05
|  | Tie down of Primary circuits |  | 2 | 2026-10-06 | 2026-10-07
|  | Tie down of catcher circuits |  | 3 | 2026-10-06 | 2026-10-08
|  | Testing of Cables |  | 1 | 2026-10-09 | 2026-10-09
|  | QC of Aisle |  | 1 | 2026-10-09 | 2026-10-09
|  | Upload Fit |  | 1 | 2026-10-09 | 2026-10-09
|  | Panel 17- 60 No Cables |  |  | 2026-10-01 | 2026-10-14
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-01 | 2026-10-01
|  | Pull in Primary Circuits |  | 1 | 2026-10-01 | 2026-10-01
|  | Pull in Catcher circuits |  | 2 | 2026-10-02 | 2026-10-05
|  | Tie down of Primary circuits |  | 2 | 2026-10-09 | 2026-10-12
|  | Tie down of catcher circuits |  | 3 | 2026-10-09 | 2026-10-13
|  | Testing of Cables |  | 1 | 2026-10-14 | 2026-10-14
|  | QC of Aisle |  | 1 | 2026-10-14 | 2026-10-14
|  | Upload Fit |  | 1 | 2026-10-14 | 2026-10-14
|  | Panel 21- 60 No Cables |  |  | 2026-10-01 | 2026-10-09
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-01 | 2026-10-01
|  | Pull in Primary Circuits |  | 1 | 2026-10-01 | 2026-10-01
|  | Pull in Catcher circuits |  | 2 | 2026-10-02 | 2026-10-05
|  | Tie down of Primary circuits |  | 2 | 2026-10-06 | 2026-10-07
|  | Tie down of catcher circuits |  | 3 | 2026-10-06 | 2026-10-08
|  | Testing of Cables |  | 1 | 2026-10-09 | 2026-10-09
|  | QC of Aisle |  | 1 | 2026-10-09 | 2026-10-09
|  | Upload Fit |  | 1 | 2026-10-09 | 2026-10-09
|  | Panel 23- 52 No Cables |  |  | 2026-10-01 | 2026-10-14
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-01 | 2026-10-01
|  | Pull in Primary Circuits |  | 1 | 2026-10-01 | 2026-10-01
|  | Pull in Catcher circuits |  | 2 | 2026-10-02 | 2026-10-05
|  | Tie down of Primary circuits |  | 2 | 2026-10-09 | 2026-10-12
|  | Tie down of catcher circuits |  | 3 | 2026-10-09 | 2026-10-13
|  | Testing of Cables |  | 1 | 2026-10-14 | 2026-10-14
|  | QC of Aisle |  | 1 | 2026-10-14 | 2026-10-14
|  | Upload Fit |  | 1 | 2026-10-14 | 2026-10-14
|  | Panel 27- 4 No Cables |  | 36 | 2026-10-15 | 2026-10-23 | 2
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-15 | 2026-10-15
|  | Pull in Primary Circuits |  | 1 | 2026-10-15 | 2026-10-15
|  | Pull in Catcher circuits |  | 2 | 2026-10-16 | 2026-10-19
|  | Tie down of Primary circuits |  | 2 | 2026-10-20 | 2026-10-21
|  | Tie down of catcher circuits |  | 3 | 2026-10-20 | 2026-10-22
|  | Testing of Cables |  | 1 | 2026-10-23 | 2026-10-23
|  | QC of Aisle |  | 1 | 2026-10-23 | 2026-10-23
|  | Upload Fit |  | 1 | 2026-10-23 | 2026-10-23
|  | Panel 31- 56 No Cables |  |  | 2026-10-15 | 2026-10-28
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-15 | 2026-10-15
|  | Pull in Primary Circuits |  | 1 | 2026-10-15 | 2026-10-15
|  | Pull in Catcher circuits |  | 2 | 2026-10-16 | 2026-10-19
|  | Tie down of Primary circuits |  | 2 | 2026-10-23 | 2026-10-26
|  | Tie down of catcher circuits |  | 3 | 2026-10-23 | 2026-10-27
|  | Testing of Cables |  | 1 | 2026-10-28 | 2026-10-28
|  | QC of Aisle |  | 1 | 2026-10-28 | 2026-10-28
|  | Upload Fit |  | 1 | 2026-10-28 | 2026-10-28
|  | Panel 33- 68 No Cables |  |  | 2026-10-15 | 2026-10-14
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-15 | 2026-10-15
|  | Pull in Primary Circuits |  | 1 | 2026-10-15 | 2026-10-15
|  | Pull in Catcher circuits |  | 2 | 2026-10-16 | 2026-10-19
|  | Tie down of Primary circuits |  | 2 | 2026-10-20 | 2026-10-21
|  | Tie down of catcher circuits |  | 3 | 2026-10-20 | 2026-10-22
|  | Testing of Cables |  | 1 | 2026-10-23 | 2026-10-23
|  | QC of Aisle |  | 1 | 2026-10-23 | 2026-10-23
|  | Upload Fit |  | 1 | 2026-10-23 | 2026-10-23
|  | Panel 35- 60 No Cables |  | 39 | 2026-10-15 | 2026-10-28
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-15 | 2026-10-15
|  | Pull in Primary Circuits |  | 1 | 2026-10-15 | 2026-10-15
|  | Pull in Catcher circuits |  | 2 | 2026-10-16 | 2026-10-19
|  | Tie down of Primary circuits |  | 2 | 2026-10-23 | 2026-10-26
|  | Tie down of catcher circuits |  | 3 | 2026-10-23 | 2026-10-27
|  | Testing of Cables |  | 1 | 2026-10-28 | 2026-10-28
|  | QC of Aisle |  | 1 | 2026-10-28 | 2026-10-28
|  | Upload Fit |  | 1 | 2026-10-28 | 2026-10-28
|  | Panel 39- 64 No Cables |  |  | 2026-10-29 | 2026-10-28 | 3
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-29 | 2026-10-29
|  | Pull in Primary Circuits |  | 1 | 2026-10-29 | 2026-10-29
|  | Pull in Catcher circuits |  | 2 | 2026-10-30 | 2026-11-02
|  | Tie down of Primary circuits |  | 2 | 2026-11-03 | 2026-11-04
|  | Tie down of catcher circuits |  | 3 | 2026-11-03 | 2026-11-05
|  | Testing of Cables |  | 1 | 2026-11-06 | 2026-11-06
|  | QC of Aisle |  | 1 | 2026-11-06 | 2026-11-06
|  | Upload Fit |  | 1 | 2026-11-06 | 2026-11-06
|  | Panel 41- 12 No Cables |  |  | 2026-10-29 | 2026-11-11
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-29 | 2026-10-29
|  | Pull in Primary Circuits |  | 1 | 2026-10-29 | 2026-10-29
|  | Pull in Catcher circuits |  | 2 | 2026-10-30 | 2026-11-02
|  | Tie down of Primary circuits |  | 2 | 2026-11-06 | 2026-11-09
|  | Tie down of catcher circuits |  | 3 | 2026-11-06 | 2026-11-10
|  | Testing of Cables |  | 1 | 2026-11-11 | 2026-11-11
|  | QC of Aisle |  | 1 | 2026-11-11 | 2026-11-11
|  | Upload Fit |  | 1 | 2026-11-11 | 2026-11-11
|  | Panel 45- 36 No Cables |  |  | 2026-10-29 | 2026-10-28
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-29 | 2026-10-29
|  | Pull in Primary Circuits |  | 1 | 2026-10-29 | 2026-10-29
|  | Pull in Catcher circuits |  | 2 | 2026-10-30 | 2026-11-02
|  | Tie down of Primary circuits |  | 2 | 2026-11-03 | 2026-11-04
|  | Tie down of catcher circuits |  | 3 | 2026-11-03 | 2026-11-05
|  | Testing of Cables |  | 1 | 2026-11-06 | 2026-11-06
|  | QC of Aisle |  | 1 | 2026-11-06 | 2026-11-06
|  | Upload Fit |  | 1 | 2026-11-06 | 2026-11-06
|  | Panel 47- 24 No Cables |  |  | 2026-10-29 | 2026-11-11
|  | Bring cables From ER Room to Panel location |  | 1 | 2026-10-29 | 2026-10-29
|  | Pull in Primary Circuits |  | 1 | 2026-10-29 | 2026-10-29
|  | Pull in Catcher circuits |  | 2 | 2026-10-30 | 2026-11-02
|  | Tie down of Primary circuits |  | 2 | 2026-11-06 | 2026-11-09
|  | Tie down of catcher circuits |  | 3 | 2026-11-06 | 2026-11-10
|  | Testing of Cables |  | 1 | 2026-11-11 | 2026-11-11
|  | QC of Aisle |  | 1 | 2026-11-11 | 2026-11-11
|  | Upload Fit |  | 1 | 2026-11-11 | 2026-11-11
Formulas:
Finish date = WORKDAY([Start Date],[No Of Days]-1,0)
Start Date = [Start Date, row above]
Start Date = [Finish date, row above]+1

## Manloader
Date | No Of Men Required | Acctual No Of Men | Offset | Working Week
2026-09-01 | 14 |  | 14 | WW36
2026-09-02 | 14 |  | 14
2026-09-03 | 14 |  | 14
2026-09-04 | 14 |  | 14
2026-09-07 | 14 |  | 14 | WW37
2026-09-08 | 14 |  | 14
2026-09-09 | 14 |  | 14
2026-09-10 | 14 |  | 14 |  | 354
2026-09-11 | 14 |  | 14 | WW38 | 8
2026-09-14 | 14 |  | 14 |  | 2832
2026-09-15 | 14 |  | 14
2026-09-16 | 14 |  | 14
2026-09-17 | 14 |  | 14 | WW39
2026-09-18 | 14 |  | 14
2026-09-21 | 14 |  | 14
2026-09-22 | 14 |  | 14
2026-09-23 | 14 |  | 14 | WW40
2026-09-24 | 14 |  | 14
2026-09-25 | 14 |  | 14
2026-09-28 | 14 |  | 14
2026-09-29 | 6 |  | 6 | WW41
2026-09-30 | 6 |  | 6
2026-10-01 | 34 |  | 34
2026-10-02 | 28 |  | 28
2026-10-05 | 28 |  | 28 | WW42
2026-10-06 | 28 |  | 28
2026-10-07 | 28 |  | 28
2026-10-08 | 28 |  | 28
2026-10-09 | 28 |  | 28 | WW43
2026-10-12 | 28 |  | 28
2026-10-13 | 28 |  | 28
2026-10-14 | 28 |  | 28
2026-10-15 | 28 |  | 28 | WW44
2026-10-16 | 28 |  | 28
2026-10-19 | 24 |  | 24
2026-10-20 | 24 |  | 24
2026-10-21 | 24 |  | 24 | WW45
2026-10-22 | 24 |  | 24
2026-10-23 | 24 |  | 24
2026-10-26 | 24 |  | 24
2026-10-27 | 24 |  | 24 | WW46
2026-10-28 | 24 |  | 24
2026-10-29 | 24 |  | 24
2026-10-30 | 24 |  | 24
2026-11-02 | 24 |  | 24 | WW47
2026-11-03 | 24 |  | 24
2026-11-04 | 24 |  | 24
2026-11-05 | 24 |  | 24
2026-11-06 | 24 |  | 24 | WW48
2026-11-09 | 24 |  | 24
2026-11-10 | 24 |  | 24
2026-11-11 | 24 |  | 24
2026-11-12 | 12 |  | 12 | WW49
2026-11-13 | 12 |  | 12
2026-11-16 | 12 |  | 12
2026-11-17 | 12 |  | 12
2026-11-18 | 12 |  | 12 | WW50
2026-11-19 | 12 |  | 12
2026-11-20 | 12 |  | 12
2026-11-23 | 0 |  | 0
Formulas:
Date = WORKDAY([Date, row above],1,0)